## README
CREDIT RISK DATA PROGRAMME — TRACKER WORKBOOK
Companion to D:\Tools\credit_risk_data\credit_risk_data_landscape.md (v2, 30-Jul-2026). Built 30-Jul-2026.
PURPOSE
A living checklist of everything planned: data sources to fetch, datasets to assemble, pipelines to build,
model prototypes, database landing places, calibration anchors, licensing constraints and open items.
Tick statuses as you progress; the Dashboard recomputes automatically.
SHEETS
Dashboard — live progress KPIs (formulas; do not type over)
1_Sources — master source checklist (108 sources: what, where, access, backfill, DB target)
2_Assembly — 7 flagship datasets to assemble (IBBI LGD, India default corpus, NBFC ECL panel, P3DH panel, district panel, anchor warehouse, synthetic books)
3_Prototypes — 12 model prototypes with their Layer-1/Layer-2 data stacks
4_Pipelines — 32 fetch/parse/load engineering tasks with anti-bot notes
5_DB_Schema — target database tables (AnaCredit/openNPL-shaped) and what feeds them
6_Anchors — 44 verified calibration numbers with as-of dates (validation targets)
7_Licensing — what each source group permits
8_Watchlist — unverified items to re-check + upcoming-release calendar
HOW TO USE
1. Work the P1 rows first (Sources, Pipelines, Assembly all carry Priority columns).
2. When you act on a row, set its Status via the dropdown: Not started -> In progress -> Fetched -> Cleaned -> Loaded -> Validated (or Done / Blocked / N/A).
3. Yellow-headed columns are yours to edit (Status, Priority, Backfill, Refresh, DB target, % complete, Notes). Other columns are reference content.
4. Statuses colour themselves: green = landed, amber = in flight, red = blocked, grey = not started.
5. Research/verification phase is COMPLETE (landscape doc v2). This workbook tracks the BUILD phase. | ID | Source | Priority | Status | Backfill plan | DB target | Notes
| S-001 | Freddie Mac SFLLD | P1 | Fetched | 1999-2025 full, sample file first | micro.facility_master | Downloaded 2026-08-02; 2 vintages parsed
EXAMPLE ROW (how a filled Sources row should look)
STATUS DEFINITIONS
Fetched = raw files landed locally. Cleaned = parsed/normalized. Loaded = in the database target.
Validated = QA'd against anchors (6_Anchors) or published totals. Done = fully operational incl. refresh.
PROVENANCE
All content compiled from credit_risk_data_landscape.md v2 (five-workstream verified research pass, 30-Jul-2026).
Numbers in 6_Anchors carry their as-of dates and sources; items flagged in 8_Watchlist were NOT verified — check before load-bearing use.
CHANGELOG
2026-07-30 Workbook created (research v1+v2 complete; build phase not started).

## 1_Sources
1. DATA SOURCES — master checklist
One row per source. Tick 'Status' as you progress; edit yellow-headed columns. Compiled 30-Jul-2026 from credit_risk_data_landscape.md v2.
ID | Region | Category | Source | Publisher | Portfolio(s) | Use for | Granularity | Frequency | Coverage / history | Access | Fetch method | Backfill plan | Refresh cadence | Priority | Status | DB target | License notes | URL | Notes
S-001 | Global | Loan-level micro | Freddie Mac Single-Family Loan-Level Dataset | Freddie Mac | Mortgage | PD, LGD, prepayment, cure, ECL | Loan-month panel | Quarterly release | 1999-Sep 2025, ~55M loans | Registration | Bulk ZIP download | Full history once (subset vintages first) | Quarterly | P1 | Not started | micro.facility_master + micro.performance_monthly + micro.recovery_cashflows | No redistribution | freddiemac.com | Expense & proceeds columns make it LGD-capable; canonical prepayment data
S-002 | Global | Loan-level micro | Fannie Mae SF Loan Performance (CAS enhanced) | Fannie Mae | Mortgage | PD, LGD, prepayment | Loan-month panel | Quarterly release | 2000+ | Registration | Bulk download | Full once | Quarterly | P2 | Not started | micro.* (same as Freddie) | No redistribution | capitalmarkets.fanniemae.com | Credit-event costs and recovery proceeds through disposition
S-003 | Global | Loan-level micro | Ginnie Mae MBS loan-level disclosure | Ginnie Mae | Mortgage (govt) | PD, delinquency | Loan-month | Monthly | 2012+ | Open | Bulk download | Optional | Monthly | P3 | Not started | micro.* | Open | ginniemae.gov | FHA/VA credit box - contrast portfolio
S-004 | Global | Loan-level micro | GSE Multifamily (Freddie MLPD + Fannie MF) | Freddie/Fannie | CRE multifamily | PD, LGD | Loan-level | Periodic | 1994+ | Registration | Download | Full once | Annual | P3 | Not started | micro.* | No redistribution | mf.freddiemac.com | Includes REO sale dates
S-005 | Global | Collateral index | FHFA HPI + NMDB aggregate statistics | FHFA | Mortgage collateral | LGD collateral paths, performance aggregates | Index: national to ZIP | Quarterly/monthly | Mid-1970s+ | Open | CSV/API | Full once | Quarterly | P1 | Not started | idx.collateral_indices | Public domain | fhfa.gov | Drives mortgage LGD stress
S-006 | Global | Loan-level micro | HMDA LAR (incl. declined applications) | FFIEC/CFPB | Mortgage | Scorecard inputs, reject inference | Application-level | Annual | 2007+ (modern format 2018+) | Open | Bulk CSV | Selected years | Annual | P2 | Not started | micro.applications | Public | ffiec.cfpb.gov | One of very few public sources of rejects
S-007 | Global | Loan-level micro | SEC ABS-EE auto loan/lease EX-102 files | Issuers via SEC EDGAR | Auto | PD, LGD, recovery timing | Loan-month XML | Monthly per deal | Nov 2016+ | Open | EDGAR scrape + XML parse | Backfill all major shelves | Monthly | P1 | Not started | micro.facility_master + micro.recovery_cashflows | Public | efts.sec.gov | Charge-off AND recovery amounts; Ford/GM/Santander/CarMax/Carvana/Westlake
S-008 | Global | Loan-level micro | CMBS ABS-EE / CREFC IRP servicer data | Issuers via SEC EDGAR | CRE | PD, LGD | Loan-level | Monthly | 2016+ | Open | XML parse | Optional | Monthly | P3 | Not started | micro.* | Public | sec.gov | Rich but lower priority vs India focus
S-009 | Global | Pool-level | Credit card master trust 10-D reports | Chase/Citi/COF/Amex via EDGAR | Cards | Vintage stress, roll rates, payment rate (EAD proxy) | Pool-month | Monthly | ~2000+ | Open | EDGAR scrape + table parse | 20y backfill | Monthly | P1 | Not started | agg.card_trust_series | Public | sec.gov | Charge-off, 30-180+ buckets, monthly payment rate, yield, excess spread
S-010 | Global | Access layer | Finsight (ABS deal browser) | Finsight | ABS all | Deal discovery | Deal-level | Live | - | Free browse; clean CSVs paid | Manual | - | - | P3 | Not started | - | Paid tier for CSV exports | finsight.com | Use raw EDGAR XML for free loan-level
S-011 | Global | Loan-level micro | European DataWarehouse (EDW) | EDW | EU retail ABS | PD/LGD; ESMA templates as schema | Loan-level | Monthly | 2012+, 100M+ loans | Paid / researcher request | - | - | - | P3 | Not started | ref.schemas (templates) | Bulk is paid | eurodw.eu | ESMA templates free = canonical EU loan-record schema
S-012 | Global | Loan-level micro | SBA 7(a) & 504 FOIA loan data | SBA | SME | PD, LGD (charge-off amounts) | Loan-level | Quarterly refresh | 1991+, ~1.79M loans | Open | CSV download | Full once | Quarterly | P1 | Not started | micro.facility_master | Public domain | data.sba.gov | Loss amounts across 3 recessions; guarantee structure caveat
S-013 | Global | Loan-level micro | LendingClub archive (incl. rejected apps) | Kaggle mirror | Personal | Application scorecard, reject inference | Loan-level | Static | 2007-2018 | Kaggle account | Kaggle download | Once | None | P1 | Not started | micro.applications | Non-commercial (mirror) | kaggle.com | Platform no longer publishes
S-014 | Global | Loan-level micro | Bondora / Go&Grow public loan book | Go&Grow OU (Estonia) | Personal | Workout LGD, cure rates, recovery cashflows | Loan-level with recovery fields | Ongoing XLSX | Feb 2009+ | Open | XLSX download + archived snapshots | Once + IEEE DataPort snapshot | Quarterly | P1 | Not started | micro.recovery_cashflows | Open-ish; API dead Sep 2025 | goandgrow.eu | EAD1/EAD2, PrincipalRecovery, InterestRecovery, RecoveryStage - unique free consumer recovery data
S-015 | Global | Loan-level micro | Prosper listings & loans | Prosper | Personal | Scorecard | Loan-level | Static-ish | 2006+ | Registration | Download | Optional | - | P3 | Not started | - | Check ToS | prosper.com | Lower priority
S-016 | Global | Loan-level micro | Kiva microloans | Kiva | Microfinance | PD-ish, inclusion | Loan-level | API | 2005+ | Open | API | Optional | - | P3 | Not started | - | Open | kiva.org | Global microfinance flavour
S-017 | Global | Loan-level micro | Home Credit Default Risk (2018) | Home Credit via Kaggle | Personal (EM) | Application scorecard structure | App + bureau + prior-app tables | Static | ~2016-18 vintage | Kaggle account | Kaggle download | Once | None | P1 | Not started | micro.applications | Competition rules: non-commercial | kaggle.com | Best structural proxy for an India retail book
S-018 | Global | Loan-level micro | Home Credit Credit Risk Model Stability (2024) | Home Credit via Kaggle | Personal (EM) | Model stability / OOT monitoring testbed | Relational, decision-dated tables | Static | Multi-year, weekly OOT splits | Kaggle account | Kaggle download | Once | None | P1 | Not started | micro.applications | Competition rules: non-commercial | kaggle.com | Gini-stability metric design; PSI/drift experiments
S-019 | Global | Loan-level micro | Amex Default Prediction (2022) | American Express via Kaggle | Cards | Behavioural PD, utilization paths | Customer-month statements (190 features) | Static | 458,913 train customers, ~5.5M rows | Kaggle account | Kaggle download | Once | None | P1 | Not started | micro.behavioural_panel | Competition rules: non-commercial | kaggle.com | Best public behavioural card panel; anonymized features
S-020 | Global | Loan-level micro | PKDD'99 Berka Czech bank dataset | CTU Prague relational repo | Retail / transactions | Transaction-feature behavioural PD | 4,500 accounts, 1.06M txns, 682 loans | Static | 1993-1998 | Open (guest DB) | MariaDB pull or Kaggle mirror | Once | None | P2 | Not started | micro.transactions | Research use | relational.fel.cvut.cz | Teaching standard for transactional/relational features
S-021 | Global | Loan-level micro | South German Credit (corrected, UCI 522) | UCI / Gromping | Personal | Teaching scorecard | Applicant-level, 1000 loans | Static | 1970s-80s | Open | Download | Once | None | P3 | Not started | - | CC BY 4.0 | archive.ics.uci.edu | Use instead of miscoded Statlog German Credit
S-022 | Global | Loan-level micro | Taiwan credit card default (UCI) | UCI | Cards | Teaching behavioural | 30k customers, 6m payment history | Static | 2005 | Open | Download | Once | None | P3 | Not started | - | Open | archive.ics.uci.edu | Classic
S-023 | Global | Loan-level micro | Give Me Some Credit (Kaggle) | Kaggle | Personal | Teaching | Applicant-level | Static | 2011 | Kaggle account | Download | Once | None | P3 | Not started | - | Non-commercial | kaggle.com | Classic
S-024 | Global | Loan-level micro | AlfaBattle 2.0 card transactions | Alfa-Bank via GitHub mirrors | Cards / transactions | Transaction-sequence PD | 4.3M transaction records | Static | ~2019-20 | Open mirrors | Download | Once | None | P3 | Not started | micro.transactions | Unclear | github.com | Russian-language docs
S-025 | Global | Aggregate benchmark | MIX Market archive (microfinance) | World Bank Data Catalog | Microfinance | MFI-level PAR30/90, write-off panel | MFI-year, 100+ countries | Static | 1999-2019 | Open | Excel/ZIP download | Once | None | P2 | Not started | agg.mfi_panel | CC BY 4.0 | datacatalog.worldbank.org | Frozen but clean; global MFI complement to India trackers
S-026 | Global | Collateral index | Manheim Used Vehicle Value Index | Cox Automotive | Auto collateral | LGD collateral paths | Index | Monthly + mid-month | 1995+ | Free download | Spreadsheet download | Once + monthly | Monthly | P2 | Not started | idx.collateral_indices | No formal open license | site.manheim.com | Auto LGD stress factor
S-027 | Global | Obligor-level PD | NUS Credit Research Initiative (CRI) | NUS RMI | Corporate | Point-in-time PD, DTD | Firm-day, 90k+ listed firms | Daily | 1990s+ | Registration (non-commercial) | Portal download | Selective (India universe) | Monthly | P2 | Not started | agg.firm_pd | Non-commercial only | nuscri.org | Covers Indian listed firms - fastest India corporate PD benchmark
S-028 | Global | Rating events | ratingshistory.info (SEC 17g-7 conversions) | Independent (SEC filings) | Corporate/SF | Transition matrices, PD term structures | Rating-event level | Ongoing | 2010+ (~1y lag) | Open | CSV download | Full once | Quarterly | P1 | Not started | ref.ratings_history | Public regulatory filings | ratingshistory.info | Build-your-own migration matrices
S-029 | Global | Obligor features | SEC EDGAR XBRL financial statements | SEC | Corporate | Scorecard features (Altman-style) | Filer-period | Quarterly | 2009+ | Open | Bulk datasets | Selective | Quarterly | P2 | Not started | ref.financials | Public | sec.gov | Pair with bankruptcy DBs for labels
S-030 | Global | Default events | FJC Integrated DB + Florida-UCLA-LoPucki BRD | FJC / UCLA | Corporate | Bankruptcy event labels | Case-level | Annual | 1980s+ | Open | Download | Once | Annual | P2 | Not started | micro.default_events | Open | fjc.gov | US corporate default labels for scorecards
S-031 | Global | Aggregate benchmark | S&P annual global default & transition study | S&P Global Ratings | Corporate | TTC PD, transition matrices | Rating-cohort tables | Annual | 1981+ (2024-data ed. Mar 2025) | Free (registration prompt) | PDF + manual table digitize | Digitize last 5 editions | Annual | P1 | Not started | agg.anchor_series | Copyright - cite, don't republish | spglobal.com | Free global corporate PD calibration layer
S-032 | Global | Aggregate benchmark | Moody's annual default study (corporate default & recovery) | Moody's | Corporate | PD to 1920, recovery by seniority | Tables | Annual | 1920+ | Registration / mirrors | PDF digitize | Latest + best mirror | Annual | P1 | Not started | agg.anchor_series | Copyright | ratings.moodys.com | Seniority-level LGD anchors; 2026 edition unconfirmed
S-033 | Global | Aggregate benchmark | Fitch + Moody's muni + Moody's project finance studies | Fitch / Moody's | Corporate, muni, infra | Niche PD/LGD (muni recovery ~67%; PF ultimate recovery ~80%) | Tables | Annual | Varies | Registration / mirrors | PDF digitize | Latest editions | Annual | P3 | Not started | agg.anchor_series | Copyright | fitchratings.com | Sec 2.11 - re-verify current editions
S-034 | Global | Aggregate benchmark | GEMs Risk Database statistics | GEMs Consortium (25 MDBs/DFIs) | EM wholesale/sovereign | EM PD + recovery priors | Counterpart-type x region x sector tables | Annual updates | 1994-2024 | Open | Web tables / PDF digitize | Once + Oct updates | Annual | P1 | Not started | agg.anchor_series | Open | gemsriskdatabase.org | Private counterparts: default 3.54%, recovery 72.9%
S-035 | Global | Aggregate benchmark | EIB sovereign & sovereign-guaranteed default/recovery stats | EIB | Sovereign | Sovereign LGD | Tables | Annual | 1994-2024 | Open | PDF | Once | Annual | P3 | Not started | agg.anchor_series | Open | eib.org | Companion to GEMs
S-036 | Global | Aggregate benchmark | ICC Trade Register | ICC | Trade finance | Product-level PD + LGD | Product x region tables | Annual | 2018-2024 | Free summary (full tables paid) | PDF digitize | Once | Annual | P2 | Not started | agg.anchor_series | Copyright summary | iccwbo.org | Only public trade-product PD+LGD
S-037 | Global | Default events | BoC-BoE Sovereign Default Database + Cruces-Trebesch haircuts | Bank of Canada / BoE | Sovereign | Default events + haircut LGD | Country-year | Annual | 1960+ | Open | Excel download | Once | Annual | P3 | Not started | agg.anchor_series | Open | bankofcanada.ca | Sovereign PD/LGD priors
S-038 | Global | Aggregate benchmark | Global Credit Data free library (LGD/EAD/downturn reports + platform docs) | GCD | Wholesale | LGD/EAD priors + wholesale default-data schema | Segment tables | Periodic (2026: Aircraft RR, Funds benchmarking) | 2000+ | Free reports (raw data member-only, banks only) | PDF digitize | Once + new releases | Semiannual | P1 | Not started | agg.anchor_series + ref.schemas | Raw pool: Basel-compliant FI members only, give-to-get | globalcreditdata.org | Unsecured LGD ~27%, secured ~22%, senior 26%/sub 38%, TTR ~1.2y
S-039 | Global | Vendor free tier | Credit Benchmark Credit Consensus Indicators | Credit Benchmark | Wholesale | Consensus-PD trend monitoring | Sector/geography indices | Monthly | ~2015+ | Free aggregates (entity feed paid) | PDF/CSV | Optional | Monthly | P3 | Not started | agg.anchor_series | Paid entity-level | creditbenchmark.com | 40+ banks' internal ratings pooled
S-040 | Global | Pool-level | ECBC Covered Bond Label HTT | ECBC | EU mortgage pools | Pool LTV distributions, arrears strata | Programme-quarter Excel | Quarterly | ~2016+ | Open, no login | Excel downloads | Selective programmes | Quarterly | P3 | Not started | agg.pool_series | Open | coveredbondlabel.com | Mortgage strata where no loan-level RMBS exists
S-041 | Global | Reference model | Japan CRD Association (SME consortium) | CRD Association | SME | Consortium design reference | - | - | 2001+ | Member-only | - | - | - | P3 | Not started | - | Closed | crd-office.net | Design template for SME data pooling
S-042 | Global | Aggregate benchmark | ELFA MLFI-25 + Equifax (ex-PayNet) SBLI/SBDI | ELFA / Equifax | Equipment & small business | Delinquency/default indices | Index | Monthly | ~2005+ | Free releases | Web/PDF | Optional | Monthly | P3 | Not started | agg.anchor_series | Copyright | elfaonline.org | Sec 2.11 - re-verify
S-043 | Global | Aggregate benchmark | Ag credit: KC Fed survey + Farm Credit System statements | KC Fed / FCA | Agriculture | Repayment indices, nonaccrual | Survey/index | Quarterly | 1980s+ | Open | Web | Optional | Quarterly | P3 | Not started | agg.anchor_series | Open | kansascityfed.org | Sec 2.11
S-044 | Global | Aggregate benchmark | Leveraged loan default summaries + revolver EAD papers | LSTA/LCD, Fed researchers, Moody's | Lev loans, corporate EAD | Default rates; CCF/utilization anchors | Articles/papers | Monthly / one-off | Index 1990s+ | Free | Manual collection | Once | Monthly | P2 | Not started | agg.anchor_series | Copyright | lsta.org | Credit Line Channel, NY Fed SR942, Boston Fed 2026, Moody's credit-line study
S-045 | Global | Regulatory disclosure | EBA Pillar 3 Data Hub (CR6/CR10 etc.) | EBA | Wholesale IRB | Cross-bank PD/LGD/RW/EL panel | Bank x exposure class x PD band | Semiannual/quarterly | Jun 2025 ref dates onward | Open | Bulk XBRL-CSV download | All available ref dates | Semiannual | P1 | Not started | agg.irb_parameters | Open | eba.europa.eu | LIVE 26 Jan 2026 - flagship new infrastructure
S-046 | Global | Regulatory disclosure | EBA EU-wide stress test CSVs (2025 + prior) | EBA | All | Stress benchmarks (PD/LGD/stage by bank) | Bank-level CSV | Biennial | 2014+ exercises | Open | CSV download | 2021/2023/2025 | Biennial | P1 | Not started | agg.stress_results | Open | eba.europa.eu | IRB CSV = labelled benchmark table
S-047 | Global | Regulatory disclosure | EBA EU-wide Transparency Exercise | EBA | All | Bank asset quality incl. IFRS9 stages | 119 banks x 4 ref dates | Annual (Dec) | 2011+ | Open | CSV download | Full history | Annual | P2 | Not started | agg.bank_panel | Open | eba.europa.eu | Workhorse bank-level dataset
S-048 | Global | Regulatory disclosure | EBA Credit Risk Benchmarking report | EBA | Wholesale IRB | IRB parameter dispersion (PD/LGD/CCF) | Asset-class tables | Annual (latest Jun 2026) | 2019+ | Open | PDF/Excel digitize | Last 3 editions | Annual | P2 | Not started | agg.irb_parameters | Open | eba.europa.eu | 'What is a reasonable PD/LGD' answer
S-049 | Global | Regulatory disclosure | EBA Risk Dashboard + risk-parameter annex | EBA | All | Stage-2 share, NPL, CoR, coverage by country | Country-quarter | Quarterly | 2014+ | Open | Interactive Excel | Full history | Quarterly | P2 | Not started | agg.stage_coverage | Open | eba.europa.eu | Q1-26: Stage 2 NFC 12.8%, HH 8.5%
S-050 | Global | Regulatory disclosure | ECB Supervisory Banking Statistics | ECB | All | Stage 1/2/3 shares + coverage by country/size | Country/size-class quarter | Quarterly | 2015+ | Open | CSV (ECB Data Portal) | Full history | Quarterly | P1 | Not started | agg.stage_coverage | Open | data.ecb.europa.eu | IFRS9 stage-migration benchmarks
S-051 | Global | Methodology | EBA IFRS 9 monitoring reports | EBA | ECL methodology | SICR/ECL design practices | Reports | Periodic | 2017+ | Open | PDF | Once | Ad hoc | P3 | Not started | docs library | Open | eba.europa.eu | Free ECL methodology handbook
S-052 | Global | Schema template | ECB AnaCredit documentation (+ openNPL / EBA NPL templates) | ECB / EBA / Open Risk | Schema | Facility-level data model; defaulted-asset schema | ~100 attributes; NPL templates | - | - | Open | PDF/GitHub | Once | - | P1 | Not started | ref.schemas | Open | ecb.europa.eu | Build target schema; openNPL = Django implementation
S-053 | Global | Aggregate benchmark | Banca d'Italia bad-loan recovery-rate notes (No. 48) | Banca d'Italia | Corporate/NPL | Workout LGD time series | Year x collateral x channel + Excel appendix | Annual | 2006-2024 | Open | Excel/PDF | Full series | Annual | P1 | Not started | agg.anchor_series | Open | bancaditalia.it | 2024 avg recovery 41% (sec 44 / unsec 37); sale price 24% GBV
S-054 | Global | Stress/scenario | Fed DFAST results + supervisory scenarios | Federal Reserve | All US | Stressed loss rates + macro paths | Bank/portfolio + scenario variables | Annual | 2013+ | Open | CSV/PDF | Full history | Annual | P1 | Not started | agg.stress_results + scen.macro_paths | Public | federalreserve.gov | 2026: ~$708bn projected losses
S-055 | Global | Aggregate benchmark | Fed charge-off & delinquency rates (+FRED) | Federal Reserve | All US | Macro-satellite fitting series | Loan type x bank size, quarterly | Quarterly | 1985+ | Open | FRED API | Full history | Quarterly | P1 | Not started | agg.anchor_series | Public | federalreserve.gov | Best free PD/LGD-to-macro series
S-056 | Global | Regulatory filings | FFIEC Call Reports (RC-C/RC-N/RI-B) | FFIEC | All US banks | Bank-level PD + recovery proxies | Bank-quarter | Quarterly | 1984+ | Open | Bulk download | Selective | Quarterly | P2 | Not started | agg.bank_panel | Public | cdr.ffiec.gov | Charge-offs AND recoveries
S-057 | Global | Regulatory filings | NCUA credit union call reports | NCUA | Credit unions | Delinquency/charge-off by loan type | CU-quarter ZIPs | Quarterly | 1994+ | Open | Bulk ZIPs | Selective | Quarterly | P3 | Not started | agg.bank_panel | Public | ncua.gov
S-058 | Global | Regulatory filings | FDIC BankFind Suite API + QBP | FDIC | US banks | Loss cross-sections | Bank-quarter | Quarterly | 1992+ | Open | REST API | Selective | Quarterly | P2 | Not started | agg.bank_panel | Public | banks.data.fdic.gov | No-auth API
S-059 | Global | Aggregate benchmark | Philadelphia Fed large-bank card & mortgage data (Y-14M) | Philadelphia Fed | Cards, Mortgage | EAD/utilization/payment-rate anchors by score band | Score-band series | Quarterly | 2012+ | Open | CSV + FRED | Full history | Quarterly | P1 | Not started | agg.anchor_series | Public | philadelphiafed.org | Best public EAD/CCF anchor; 67 new series Jul 2025
S-060 | Global | Aggregate benchmark | CFPB Consumer Credit Trends + CARD Act report | CFPB | Consumer | Origination mix, utilization/CLIP/payment tiers | Score-tier series | Ongoing / biennial | 2005+ (CARD Act 2025 ed.) | Open | CSV/PDF | Full | Biennial | P2 | Not started | agg.anchor_series | Public domain | consumerfinance.gov | 15% of GP cardholders minimum-paying (2025)
S-061 | Global | Aggregate benchmark | NY Fed Household Debt & Credit (CCP aggregates) | NY Fed | Consumer | Delinquency transition rates by product | Product-quarter | Quarterly | 1999+ | Open | Excel | Full | Quarterly | P2 | Not started | agg.anchor_series | Public | newyorkfed.org | Micro panel restricted
S-062 | Global | Schema template | FR Y-14Q Schedule H.1 instructions | Federal Reserve | Wholesale schema | Facility-level field definitions | Field spec | - | - | Open | PDF | Once | - | P2 | Not started | ref.schemas | Public | reginfo.gov | What a bank corporate credit system must hold
S-063 | Global | Aggregate benchmark | OCC Mortgage Metrics + FSA student aid data | OCC / FSA | Mortgage, Student | Servicer performance; cohort default rates | Aggregate | Quarterly | 2008+ | Open | PDF/CSV | Optional | Quarterly | P3 | Not started | agg.anchor_series | Public | studentaid.gov | FSA: institution-level nonpayment rates since Jul 2025
S-064 | Global | Stress/scenario | BoE Bank Capital Stress Test 2025 + scenario key elements | Bank of England | UK all | Bank-level stressed impairments + macro paths | 7 banks, bank-level | Biennial | 2014+ (2025 pub Dec 2025) | Open | PDF/Excel | 2025 + archive | Biennial | P2 | Not started | agg.stress_results + scen.macro_paths | Open | bankofengland.co.uk | 2026 expected desk-based aggregate-only
S-065 | Cross-country | Aggregate benchmark | IMF Financial Soundness Indicators | IMF | Country-level | NPL/provisions/capital panel | Country-quarter | Quarterly | 2005+ | Open | SDMX API | Full | Quarterly | P2 | Not started | agg.country_panel | Open | data.imf.org | India included
S-066 | Cross-country | Aggregate benchmark | OECD Financing SMEs Scoreboard 2026 | OECD | SME | SME NPL rates ~50 countries | Country-year | Annual | 2007-2024 | Open | Excel | Full | Annual | P2 | Not started | agg.country_panel | Open | oecd.org | SME benchmark corridor
S-067 | Cross-country | Aggregate benchmark | BIS credit to NFS, credit gaps, DSRs | BIS | Macro | Early-warning features | Country-quarter | Quarterly | 1960s+ | Open | Bulk CSV/SDMX | Full | Quarterly | P2 | Not started | agg.country_panel | Open | data.bis.org | India included
S-068 | Cross-country | Aggregate benchmark | World Bank GFDD | World Bank | Macro-financial structure | Structure indicators | Country-year | Static (to 2021) | 1960-2021 | Open | Excel | Once | - | P3 | Not started | agg.country_panel | CC BY | worldbank.org | Stale - structure only
S-069 | Cross-country | Aggregate benchmark | Doing Business Resolving Insolvency archive + B-READY | World Bank | Corporate LGD | Recovery cents-on-dollar by country | Country-year | Static (archive) | 2004-2019 (B-READY 2025) | Open | Archive download | Once | - | P2 | Not started | agg.country_panel | Open | archive.doingbusiness.org | Cross-country LGD prior + regime scores
S-070 | Cross-country | Stress anchor | Laeven-Valencia systemic banking crises DB (2026 update) | IMF | Stress tails | Peak NPL, fiscal cost, output loss per crisis | Crisis-episode level | Updated 2026 | 1970-2025 | Open | WP dataset download | Once | Ad hoc | P1 | Not started | agg.crisis_episodes | Open | imf.org | Median peak NPL ~11% AE / ~30% EM
S-071 | Cross-country | Stress anchor | ESRB European financial crises database | ESRB/ECB | Stress | EU crisis episode dating | Episode-level | Static (2021) | 1970-2021 | Open | Download | Once | - | P3 | Not started | agg.crisis_episodes | Open | esrb.europa.eu | Scenario dating labels
S-072 | Cross-country | Stress/scenario | NGFS climate scenarios (Phase V + short-term) | NGFS / IIASA | Climate | Climate-credit stress paths | Scenario variables by sector/country | Per phase | Projections to 2100; ST 5y | Open | IIASA portal download | Current vintages | Per phase | P2 | Not started | scen.climate_paths | Open | ngfs.net | Phase VI end-2026 - physical-risk overhaul
S-073 | EM | Aggregate benchmark | Brazil BCB: SGS API + SCR.data + IF.data | Banco Central do Brasil | EM comparator | Delinquency by product/state/segment | ~700k monthly series from credit register | Monthly | Jun 2012+ (SGS older) | Open | REST API (no key) | Selective series | Monthly | P2 | Not started | agg.em_comparators | Open | opendata.bcb.gov.br | Design benchmark for credit-register data products
S-074 | EM | Aggregate benchmark | Other EM regulators (CNBV, SBS, CMF, SFC, BDDK, OJK, BSP, SARB BA900, NCR, CBK) | Various | EM comparators | NPL by product/sector/bank | Country tables | Monthly/quarterly | Varies | Open | Web/Excel per regulator | Selective | Quarterly | P3 | Not started | agg.em_comparators | Open | bddk.org.tr | Split into separate rows if/when used
S-075 | Cross-country | Access programme | EU credit-register research access (Bundesbank RDSC, BdE BELab, BdP BPLIM, BdF/CASD) | NCBs | Wholesale micro | Registry-grade loan-level methodology work | Loan-level (controlled) | - | - | Approved research projects | Application process | - | - | P3 | Not started | - | Controlled environments; BPLIM has remote execution | bplim.bportugal.pt | Develop methodology in EU, transfer method (not data) to India
S-076 | India | Regulatory report | RBI Financial Stability Report (semiannual) | RBI | All India | Stress anchors, SMA staging, sector GNPA, scenario annex | System/sector/large-borrower tables | Semiannual | 2010+ (latest Jun 2026) | Open (PDFs bot-gated) | Manual download + table extract | 10y backfill | Semiannual | P1 | Not started | agg.india_anchor_series + scen.macro_paths | Open | rbidocs.rbi.org.in | GNPA 1.8% Mar-26; PSB retail SMA 9.4%; adverse CRAR ~13%
S-077 | India | Regulatory report | RBI Report on Trend & Progress of Banking | RBI | All India | Recovery by channel, NPA movement, slippage | Annual tables | Annual (Dec) | 1990s+ | Open | PDF extract | 10y | Annual | P1 | Not started | agg.india_anchor_series | Open | rbi.org.in | FY25: IBC 37%, SARFAESI 31.5%, Lok Adalat 2.4%
S-078 | India | Statistical portal | RBI DBIE/CIMS: BSR-1, sectoral deployment, STRBI | RBI | All India | District/sector credit, interest-rate buckets, bank-wise annual | District/sector/bank series | Quarterly/monthly/annual | BSR from 1972 | Open | Portal CSV/XLSX export | Full available history | Quarterly | P1 | Not started | agg.india_geo_panel | Open | data.rbi.org.in | Rate-bucket cut = closest public risk-based-pricing data
S-079 | India | Government data | data.gov.in NPA datasets + parliamentary question annexures | GoI / Parliament | All India | Bank-wise NPA, write-offs, recovery | Bank-year tables | Ad hoc | 2015+ | Open | CSV/PDF (eparlib) | Full available | Ad hoc | P2 | Not started | agg.bank_panel_india | Open | data.gov.in | Write-offs Rs 8.9 lakh cr (5y + H1FY26)
S-080 | India | Loan-level micro | IBBI quarterly newsletters - Table 5 case-level CIRP outcomes | IBBI | Corporate India | Workout LGD micro data (company-named) | Case-level: claims, liq/fair value, realisation, dates | Quarterly | 2017+ (~1,400 resolutions) | Open | PDF table extraction | ALL quarters (flagship backfill) | Quarterly | P1 | Not started | micro.default_events + micro.recovery_cashflows | Open | ibbi.gov.in | India's only public workout-LGD micro dataset
S-081 | India | Aggregate benchmark | NeSL default statistics (IU newsletters) | NeSL | Corporate/MSME India | Contractual default incidence by ticket size/segment | Segment tables | Quarterly | ~2020+ | Open | PDF extract | All editions | Quarterly | P2 | Not started | agg.india_anchor_series | Open | nesl.co.in | Corporate defaults ~3.75% of corporate debt
S-082 | India | Default registry | CIC public defaulter registries (CIBIL, Experian, CRIF, Equifax) | CICs per RBI Master Direction | Corporate India | Default labels: suit-filed >=Rs 1 cr, wilful >=Rs 25 lakh | Borrower-level (search-only) | Monthly submissions | Regime since Nov 2024 (older archives) | Search-only, no bulk | Careful throttled search (Experian most tolerant; CIBIL blocks bots) | Protocol + legal review first | Quarterly | P2 | Not started | ref.entities + micro.default_events | ToS caution | suit.experian.in | Public borrower-level default data for India corporates
S-083 | India | Bond reference | NSDL indiabondinfo + CDSL corporate bond DBs | NSDL/CDSL | Corporate bonds India | ISIN terms, rating details | ISIN-level | Live | - | Open (no bulk) | Per-ISIN scrape | Selective universe | Monthly | P3 | Not started | ref.instruments_bonds | Open | indiabondinfo.nsdl.com | Rating-history depth unverified
S-084 | India | Rating events | NSE/BSE daily CRA rating feeds (Aug 2025+) + Reg 57 payment intimations | Exchanges / CRAs | Corporate India | Daily rating actions incl. D; bond payment status | Event-level Excel + announcements | Daily | Feeds Aug 2025+; announcements older | Open | Feed download + announcement scrape | Aug 2025+; pre-history via announcements | Daily/weekly | P1 | Not started | ref.rating_events_daily | Open | nseindia.com | Machine-readable default-event feed
S-085 | India | Rating history | CRA SEBI website disclosures: Annexure V (rating history) + VI (defaults) | CRISIL/ICRA/CARE/IndRa/Acuite/Brickwork/Infomerics | Corporate India | Issuer-level rating histories + default lists | Issuer/instrument Excel, half-yearly | Half-yearly, 10y archives | ~2016+ | Open | Excel collection across 7 CRAs | Full archives | Half-yearly | P1 | Not started | ref.ratings_history + micro.default_events | Regulatory disclosure | crisilratings.com | THE entity-level default label source (not study annexures)
S-086 | India | Aggregate benchmark | CRA annual default & transition studies | CRISIL/ICRA/CARE/India Ratings | Corporate India | CDRs + transition matrices by rating | Rating-category tables | Annual | FY2010s+ (CRISIL FY25 out) | Open | PDF digitize | 5y per CRA | Annual | P1 | Not started | agg.anchor_series | Copyright - cite | crisilratings.com | Cross-CRA calibration differences are informative
S-087 | India | Aggregate benchmark | CGTMSE annual report + MSME dashboard claims data | CGTMSE | MSME India | Guarantee claims = default-cost proxy | Scheme/state-year | Annual | 2000+ | Open | PDF/dashboard extract | 10y | Annual | P2 | Not started | agg.india_anchor_series | Open | cgtmse.in | FY25 guarantees ~Rs 64,142 cr
S-088 | India | Aggregate benchmark | MUDRA/PMMY NPA disclosures | MUDRA / PQ answers | Micro-enterprise India | NPA by scheme category | Category-year | Annual / ad hoc | 2015+ | Open | PDF/PQ extract | Full | Annual | P3 | Not started | agg.india_anchor_series | Open | mudra.org.in | PSB Mudra NPA 3.4% FY24
S-089 | India | Collateral index | NHB RESIDEX housing price index | NHB | Housing collateral | City-level HPI for mortgage LGD | City-quarter, 50+ cities | Quarterly | 2017 rebase (2007 legacy) | Open | Portal download | Full | Quarterly | P2 | Not started | idx.collateral_indices | Open | residex.nhbonline.org.in | India mortgage LGD stress factor
S-090 | India | Regulatory report | NHB Report on Trend & Progress of Housing | NHB | Housing India | HFC GNPA by segment | Segment-year | Annual (latest Feb 2026) | 2000s+ | Open | PDF extract | 5y | Annual | P2 | Not started | agg.india_anchor_series | Open | nhb.org.in | HFC GNPA 2.32% Mar-24
S-091 | India | Aggregate benchmark | ARC/SR recoveries: CRISIL SR study + RBI T&P ARC tables | CRISIL / RBI | Distressed India | SR redemption rates | Cohort tables | Ad hoc / annual | 2019+ | Open | PDF extract | Once | Annual | P3 | Not started | agg.india_anchor_series | Copyright | crisilratings.com | SR recovery 65-70% FY25E
S-092 | India | Aggregate benchmark | NAFSCOB co-operative bank data (StCB/DCCB/PACS) | NAFSCOB | Co-op India | NPA & recovery ratios state-wise | State-year | Annual | 1990s+ | Open | PDF extract | 5y | Annual | P3 | Not started | agg.india_geo_panel | Open | nafscob.org | Rural/co-op segment
S-093 | India | Bureau publication | TransUnion CIBIL Credit Market Indicator (CMI) | TU CIBIL | Retail India | Delinquency by product & risk tier | Product/tier-quarter | Quarterly | 2021+ (Mar-26 ed.) | Open PDF | PDF digitize | Full archive | Quarterly | P1 | Not started | agg.india_anchor_series | Copyright - model from, don't republish | transunioncibil.com | CMI 102; home-loan delinq 0.7-0.8%
S-094 | India | Bureau publication | SIDBI x TU CIBIL MSME Pulse | SIDBI / TU CIBIL | MSME India | NPA by ticket/segment/lender/CMR tier | Segment-quarter | Quarterly (Jul-26 ed.) | 2018+ | Open PDF | PDF digitize | Full archive | Quarterly | P1 | Not started | agg.india_anchor_series | Copyright | sidbi.in | Commercial credit <Rs 50 cr: Rs 35.2 lakh cr
S-095 | India | Bureau publication | CRIF How India Lends + MicroLend (+ monthly Lite) | CRIF High Mark | Retail & MFI India | PAR by product/ticket/state/district | Product/state tables | Annual + quarterly/monthly | 2019+ (May-26 eds.) | Open PDF | PDF digitize | Full archive | Quarterly | P1 | Not started | agg.india_anchor_series + agg.india_geo_panel | Copyright | crifhighmark.com | FY26 retail PAR 3.1% (from 3.6%)
S-096 | India | Industry tracker | MFIN Micrometer | MFIN | Microfinance India | PAR 31-180 by state | State-quarter | Quarterly (57th ed. Q4 FY26) | 2012+ | Open PDF | PDF digitize | All 57 editions | Quarterly | P1 | Not started | agg.india_geo_panel | Copyright | mfinindia.org | PAR 31-180: 2.0% Mar-26 vs 6.3% Mar-25 - full cycle
S-097 | India | Industry tracker | Sa-Dhan Bharat Microfinance Report | Sa-Dhan (+NABARD) | Microfinance India | PAR30+/90+ by state | State-year | Annual (2025 ed. = FY25) | 2000s+ | Summary free | PDF digitize | 5y | Annual | P2 | Not started | agg.india_geo_panel | Copyright | sa-dhan.net | Perimeter differs from MFIN - note when mixing
S-098 | India | Industry tracker | SIDBI x Equifax Microfinance Pulse | SIDBI / Equifax | Microfinance India | Delinquency trends | Segment-quarter | Quarterly (Vol XXVII Jun-26) | 2019+ | Open PDF | PDF digitize | Full archive | Quarterly | P2 | Not started | agg.india_anchor_series | Copyright | assets.equifax.com | Delinquency 6.64% Mar-25 to 2.35% Mar-26
S-099 | India | Industry tracker | FACE Fintech Personal Loans (quarterly) | FACE (SRO-FT) | Digital PL India | 90+ DPD by tier/geography | Segment-quarter | Quarterly | 2022+ | Open PDF | PDF digitize | Full archive | Quarterly | P2 | Not started | agg.india_anchor_series | Copyright | faceofindia.org | 90+ DPD 3.6% Mar-25; tier-3 4.2%
S-100 | India | Regulatory report | NABARD Status of Microfinance in India (SHG-BLP) | NABARD | SHG India | SHG NPA by state/agency | State-year | Annual (FY24 latest verified) | 2010s+ | Open | PDF digitize | 5y | Annual | P3 | Not started | agg.india_geo_panel | Open | nabard.org | SHG NPA 2.12% FY24; FY25 edition unconfirmed
S-101 | India | Government data | SLBC agenda/minutes (Kerala, Punjab, West Bengal pilots) | State SLBCs | All India | District-wise NPA, recovery certificates, SARFAESI cases | District tables inside PDFs | Quarterly meetings | Varies by state | Open | PDF extract (format varies) | 2-3y pilots then expand states | Quarterly | P2 | Not started | agg.india_geo_panel | Open | slbckerala.com | Hidden district-level NPA dataset
S-102 | India | Company disclosures | NBFC Ind AS 109 ECL notes (top 50 annual reports) + Chola ECL methodology doc | NBFCs | All NBFC India | Stage-wise EAD/ECL by product, PD/LGD assumptions, scenario weights | NBFC x product x year | Annual | FY2019+ (7+ years) | Open | AR PDF extraction (LLM-assisted + QA) | FY19-FY26 across ~50 NBFCs | Annual | P1 | Not started | agg.nbfc_ecl_panel | Copyright ARs - extract facts | files.cholamandalam.com | FLAGSHIP: the only India ECL calibration set; Bajaj/Chola/Shriram verified
S-103 | India | Pool-level | PTC pool surveillance rationales (4 CRAs) | CRISIL/ICRA/IndRa/CARE | Retail ABS India | Pool CCE, 90+/180+ dpd, CE utilisation | Pool-review level | Ongoing | 2015+; FY26 volume Rs 2.55 lakh cr | Open | Rationale PDF scrape | 3y pilot | Monthly | P2 | Not started | agg.pool_series_india | Copyright | icra.in | Real Indian retail vintage performance by originator
S-104 | India | Loan-level micro | LTFS FinHack datasets (1: vehicle default; 3: bureau behavioural) | L&T Financial Services via Kaggle/AV | Vehicle & retail India | India application scorecard micro data | Loan-level ~233k, ~40 fields incl. CIBIL score | Static | 2019 / 2021 vintages | Kaggle/AV account | Download (mirrors live) | Once | None | P1 | Not started | micro.applications_india | Hackathon terms: non-commercial | kaggle.com | The only real India loan-level tape; FinHack 2 is NOT default data
S-105 | India | Platform disclosures | NBFC-P2P monthly portfolio disclosures (LenDenClub, Faircent, +) | P2P platforms per RBI MD | Unsecured India | Monthly NPA by age, vintage performance | Platform-month | Monthly | 2019+ | Open | Factsheet/page scrape | 2-3y | Monthly | P3 | Not started | agg.india_anchor_series | Copyright | lendenclub.com | RBI-mandated disclosure; formats vary
S-106 | India | Corporate financials | MCA master data + AOC-4/XBRL financials | MCA | Corporate India | Scorecard features | Entity/filing level | Live | 2006+ | Master free; Rs 100/company/year for filings | Portal or resellers (Probe42/Tofler) | Targeted: defaulted entities + matched sample | Ad hoc | P2 | Not started | ref.financials_india | Per-document fees | mca.gov.in | No confirmed bulk product on V3
S-107 | India | Corporate financials | screener.in / exchange XBRL / CMIE Prowess | Various | Corporate India | Listed-co financials panel | Company-year | Ongoing | 10y+ | Free / paid / academic | Export/API | Selective | Quarterly | P3 | Not started | ref.financials_india | Mixed | screener.in | Prowess via academic access
S-108 | India | Regulatory reference | RBI ECL Directions 2026 + Basel III SA Directions + draft MRM guidance + RB-CRIS | RBI | Regulatory spec | Build-target requirements (floors, SICR, glide path) | Documents | One-time + updates | Issued Apr 2026; effective 1 Apr 2027 | Open | Manual | - | Ad hoc | P1 | Not started | docs library | Open | assets.kpmg.com | Floors: Stage-1 ~0.40%, Stage-2 ~5%; 30-dpd SICR
S-109 | India | Ecosystem stats | Sahamati Account Aggregator statistics | Sahamati | Underwriting rail | AA adoption trajectory | Ecosystem counts | Ongoing | 2021+ | Open | Web | - | Quarterly | P3 | Not started | docs library | Open | sahamati.org.in | ~24 cr consents; future cash-flow underwriting rail

## Dashboard
CREDIT RISK DATA PROGRAMME — DASHBOARD
All figures computed live from the tracker sheets. Update Status columns there; this page follows.
HEADLINE |  |  |  | SOURCES: STATUS x PRIORITY
Data sources tracked |  | 109 |  | Priority | Not started | In progress | Fetched | Cleaned | Loaded | Validated | Done | Blocked | N/A | Total
Sources done (Loaded/Validated/Done) |  | 0 |  | P1 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38
Sources in flight (In progress/Fetched/Cleaned) |  | 0 |  | P2 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37
Source completion % |  | 0% |  | P3 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34
Pipelines done |  | 0
Assembly projects done |  | 0 |  | SOURCES BY REGION | Total | Done
Prototypes done |  | 0 |  | Global | 64 | 0
Watchlist open items |  | 18 |  | India | 34 | 0
|  |  |  | EM | 2 | 0
|  |  |  | Cross-country | 9 | 0
WORKSTREAM PROGRESS
Workstream | Total | Not started | In flight | Done
1. Sources | 109 | 109 | 0 | 0
2. Assembly projects | 7 | 7 | 0 | 0
3. Prototypes | 12 | 12 | 0 | 0
4. Pipelines | 32 | 32 | 0 | 0
5. DB tables | 16 | 16 | 0 | 0
8. Watchlist | 18 | 18 | 0 | 0

## 2_Assembly
2. ASSEMBLY PROJECTS — the differentiated datasets to build
Five flagship datasets nobody has assembled + the anchor warehouse + synthesis. Research phase is complete; build phase starts now.
ID | Project | Description | Doc ref | Research status | Layer-1 inputs | Layer-2 anchors | Key steps | Deliverable | Dependencies | Priority | Build status | % complete | Notes
AP-1 | IBBI case-level corporate LGD dataset | Extract Table 5 (CIRPs yielding resolution) + liquidation tables from every IBBI quarterly newsletter into a company-named workout-LGD dataset (~1,400 resolutions) with claims, liquidation/fair values, realisation and durations. | §4.2 | Done (verified Jul-26) | IBBI quarterly newsletter PDFs (S-079) | IBBI headline ratios; T&P recovery-by-channel; GEMs | 1) Download all newsletters 2) PDF table extraction (pdfplumber/camelot) 3) Normalize entity names 4) QA vs published cumulative ratios 5) Load micro.default_events + micro.recovery_cashflows 6) Derive LGD distribution + time-to-resolution curves | India corporate workout-LGD dataset + recovery-timing curves | PL-20 | P1 | Not started | 0% | Flagship. Realisation ratios drift by quarter — record cutoff per case.
AP-2 | India corporate default-event & rating-migration corpus | Assemble issuer-level default labels + full rating histories from CRA Annexure V/VI files, daily NSE/BSE rating feeds, Reg 57 intimations and CIC defaulter registries; India's 17g-7 equivalent. | §4.2 | Done (verified Jul-26) | Annexure V/VI Excels (7 CRAs) (S-084); exchange feeds (S-083); CIC registries (S-081); indiabondinfo (S-082) | CRA default studies (CDRs, matrices) (S-085); NeSL (S-080) | 1) Collect Annexure V/VI archives 2) Normalize scales/issuer names across CRAs 3) Ingest daily exchange rating feeds from Aug-25 4) Scrape Reg 57 announcements 5) Entity-resolve vs CIC registries 6) Build migration matrices + default-event table 7) Validate vs published CDRs | Issuer-level Indian rating-migration panel + default-event history | PL-22, PL-23, PL-24 | P1 | Not started | 0% | Studies do NOT name defaulters — Annexure VI does.
AP-3 | India NBFC ECL panel | Extract stage-wise gross exposure, ECL allowance, coverage, PD/LGD assumptions and scenario weights from ~50 NBFC annual reports x FY19-FY26. | §4.5 | Done (3 NBFCs verified) | NBFC annual reports (S-101); Chola ECL methodology doc | ECB/EBA stage benchmarks; RBI floors (0.40%/5%) | 1) Fix NBFC universe (~50) 2) Collect ARs FY19-FY26 3) LLM-assisted note extraction + human QA 4) Normalize product taxonomies 5) Panelize stage coverage by product-year 6) Benchmark vs EU stage data | Product-level India ECL panel (stage EAD, coverage, PD/LGD disclosures) | PL-25 | P1 | Not started | 0% | Value spikes toward Apr-2027 bank ECL deadline.
AP-4 | EU cross-bank IRB parameter panel (P3DH) | Bulk-download P3DH machine-readable Pillar 3 (CR6/CR10) and panelize EAD-weighted PD/LGD/RW/EL by bank x exposure class x PD band x ref date. | §3.1 | Done (P3DH live 26-Jan-26) | EBA P3DH bulk CSVs (S-045) | EBA benchmarking dispersion report (S-048); transparency exercise (S-047) | 1) Bulk download all ref dates 2) Parse DPM/XBRL-CSV 3) Build agg.irb_parameters 4) Dispersion analytics 5) Refresh semiannually | Cross-bank IRB PD/LGD benchmark panel + dispersion views | PL-12 | P1 | Not started | 0% | Global benchmark product; replaces PDF scraping.
AP-5 | India district-risk panel | Join SLBC district NPA tables with BSR-1 district credit (occupation x rate bucket) and state microfinance PAR into a district-level risk surface. | §4.4 | Done (KL/PB/WB verified) | SLBC minutes (S-100); BSR-1 (S-077) | MFIN/CRIF state-district PAR (S-095/094); NABARD SHG (S-099) | 1) Pilot 3 states' SLBC PDFs 2) District-name normalization (LGD codes) 3) Merge BSR-1 credit 4) Layer microfinance PAR 5) Build agg.india_geo_panel 6) Expand states | District-level India credit-risk surface (concentration, geo-stress) | PL-28, PL-29 | P2 | Not started | 0% | Unique geographic asset; useful for climate overlays later.
AP-6 | Global anchor warehouse | Digitize every benchmark table (agency studies, GEMs, GCD, BdI, ICC, Philly Fed, Fed charge-offs, EBA/ECB stage data, bureau PDFs) into one long-format anchor store with source/as-of metadata. | §3, §7.1 | Done (sources verified) | — | All Layer-2 sources (S-031..S-078, India S-075..S-107) | 1) Define agg.anchor_series long schema (source, segment, metric, period, value, asof, url) 2) Prioritized digitization backlog 3) Automated pulls where API exists 4) QA vs doc's key numbers (6_Anchors) 5) Refresh calendar | Queryable calibration-anchor database powering all prototypes | PL-10..PL-19, PL-26, PL-27 | P1 | Not started | 0% | The backbone — do early; everything validates against it.
AP-7 | India synthetic loan books (retail/MSME/corporate) | Constrained synthetic generation: fit dependence on Layer-1 micro (Home Credit/LTFS/Freddie), reweight to reproduce India Layer-2 anchors (bureau PAR, FSR, NBFC ECL panel). | §7.1 | Done (method set) | Home Credit (S-017/018); LTFS (S-103); Freddie (S-001); Bondora (S-014) | CMI/MSME Pulse/CRIF/MFIN (S-092..095); FSR (S-075); AP-3 panel | 1) Build facility schema (AnaCredit-shaped) 2) Fit copulas/CTGAN on Layer-1 3) Calibrate marginals to anchors 4) Prove reproduction of targets 5) Package as teaching/prototype datasets | Synthetic India books that provably reproduce published aggregates | AP-1, AP-3, AP-6 | P1 | Not started | 0% | SDV/CTGAN + reweighting; document constraints per book.

## 3_Prototypes
3. MODEL PROTOTYPES — starter stacks
One row per planned prototype, mapped to its Layer-1/Layer-2 data and regulatory hook (doc §7.2).
ID | Prototype | Portfolio | Doc ref | Layer-1 micro data | Layer-2 anchors | Regulatory hook | Deliverable | Depends on | Priority | Status | Notes
M-01 | Mortgage PD + LGD + prepayment pipeline | Mortgage | §7.2 | Freddie SFLLD (loss columns) (S-001) | DFAST loss rates; EBA IRB CSV; FHFA HPI paths | IFRS9/ECL lifetime, Basel IRB | End-to-end PD/LGD/prepay models + ECL engine demo | PL-01 | P1 | Not started | Validates the whole architecture first
M-02 | Auto PD + LGD + recovery timing | Auto | §7.2 | ABS-EE EX-102 (S-007); LTFS (S-103) for India scorecard | Manheim; CRIF auto/2W PAR; PTC pool rationales | RBI ECL, IFRS9 | Auto book models incl. workout-recovery timing | PL-03, PL-07 | P1 | Not started | Both geographies have micro data here
M-03 | Behavioural card + EAD/CCF | Cards | §7.2 | Amex panel (S-019); master trust 10-Ds (S-009) | Philly Fed utilization by score band; CFPB CARD Act tiers | Basel CCF, IFRS9 EAD | Behavioural PD + utilization/CCF model with anchored calibration | PL-04, PL-07, PL-10 | P1 | Not started | EAD story is anchor-based by design
M-04 | Application scorecard + stability monitoring | Personal (EM) | §7.2 | Home Credit 2018 + 2024 (S-017/018); LendingClub rejects (S-013) | NY Fed transitions; CIBIL CMI risk tiers | RBI draft MRM guidance | Scorecard + reject inference + OOT stability/PSI monitoring kit | PL-07 | P1 | Not started | 2024 set = ready-made monitoring testbed
M-05 | Unsecured consumer workout LGD + cure | Personal | §7.2 | Bondora recovery cashflows (S-014) | GCD unsecured LGD ~27%; P2P India disclosures | IFRS9 LGD, RBI ECL | Workout-LGD, cure-rate and recovery-timing models | PL-06 | P1 | Not started | Only free consumer recovery-cashflow data
M-06 | SME/MSME PD + LGD | SME/MSME | §7.2 | SBA 7(a) charge-offs (S-012) | MSME Pulse by ticket/CMR; CGTMSE claims; OECD SME NPLs; EBA SME IRB | RBI ECL (MSME book) | SME scorecard + LGD distribution + India MSME calibration | PL-05, PL-26 | P1 | Not started
M-07 | Corporate PD + rating migration | Corporate | §7.2 | ratingshistory + EDGAR XBRL + FJC (S-028/029/030); India corpus (AP-2) | S&P/Moody's studies; CRISIL/ICRA matrices; NUS-CRI; NeSL | Basel IRB, ICAAP | Transition matrices, PD term structures, Altman/Merton scorecards | AP-2, PL-16 | P1 | Not started
M-08 | Corporate LGD (India-led) | Corporate | §7.2 | IBBI Table 5 case data (AP-1) | GEMs 72.9%; GCD seniority; BdI 41%; T&P channel table | RBI ECL LGD, IFRS9 | India corporate LGD model + channel-conditional structure | AP-1 | P1 | Not started | India's unique strength
M-09 | Microfinance stress & SICR demo | Microfinance | §7.2 | (synthesize) | MFIN+Sa-Dhan+CRIF+Equifax full-cycle state panel; MIX global | RBI ECL staging/SICR | State-level stress model + SICR trigger demonstration on real cycle | PL-26, AP-6 | P2 | Not started | FY24-26 cycle = rare gift
M-10 | IFRS9 / RBI ECL engine | All-portfolio | §7.2 | Any Layer-1 for PD term structures | NBFC ECL panel (AP-3); ECB stage stats; EBA IFRS9 reports; RBI floors | RBI ECL Directions 2026 | Full 3-stage ECL engine with floors, SICR, scenario weights | AP-3, AP-6, M-01 | P1 | Not started | The commercial centerpiece for Apr-2027
M-11 | Stress testing / ICAAP suite | All-portfolio | §7.2 | — | Fed/BoE/RBI FSR scenarios; Fed charge-off satellites; Laeven-Valencia tails; NGFS climate | ICAAP, RBI FSR methodology | Macro-satellite models + scenario engine + climate overlay | PL-17, AP-6 | P1 | Not started | Validate severe vs RBI adverse range
M-12 | Wholesale IRB benchmarking tool | Wholesale | §7.2 | — | P3DH CR6 panel (AP-4); EBA benchmarking dispersion | Basel IRB validation | Benchmark-your-parameters tool vs EU bank distribution | AP-4 | P2 | Not started

## 4_Pipelines
4. PIPELINES — fetch/parse/load engineering tasks
One row per data-engineering task. Effort: S <1 day, M 1-3 days, L 1-2 weeks (order of magnitude).
ID | Task | Feeds from | Method | Tooling & anti-bot notes | Output table | Backfill range | Refresh schedule | Effort | Priority | Status | Notes
PL-01 | Freddie SFLLD downloader + loader | S-001 | Bulk ZIP -> parquet | Registration cookie; 100GB+ full history — start with sample file + selected vintages | micro.facility_master/performance/recovery | 1999-2025 | Quarterly | L | P1 | Not started | Reference pipeline for everything
PL-02 | Fannie CAS enhanced loader | S-002 | Bulk download | Similar to PL-01 | micro.* | 2000-2025 | Quarterly | M | P2 | Not started
PL-03 | ABS-EE EX-102 XML parser (auto shelves) | S-007 | EDGAR index -> 10-D exhibits -> XML | Respect SEC rate limits (10 req/s, declared UA); schema per Reg AB II | micro.facility_master/recovery | 2016+ | Monthly | L | P1 | Not started | Start: 2-3 shelves (Ford, Santander)
PL-04 | Card master-trust 10-D parser | S-009 | EDGAR scrape + table parse | Exhibit formats vary by trust; regex/table heuristics per trust | agg.card_trust_series | ~2000+ | Monthly | M | P1 | Not started | Chase + Citi first
PL-05 | SBA 7(a)/504 loader | S-012 | CSV download | Straightforward | micro.facility_master | 1991+ | Quarterly | S | P1 | Not started
PL-06 | Bondora/Go&Grow ingester | S-014 | XLSX + snapshot archives | Schema drift across vintages; API is dead | micro.recovery_cashflows | 2009+ | Quarterly | S | P1 | Not started
PL-07 | Kaggle fetcher (Amex, HC18, HC24, LC, LTFS, GMSC) | S-013/017/018/019/103 | kaggle CLI | Accept competition rules in browser first; store raw + license note | micro.* various | Static | None | S | P1 | Not started
PL-08 | Berka MariaDB pull | S-020 | SQL (guest/ctu-relational) | Public guest credentials | micro.transactions | Static | None | S | P2 | Not started
PL-09 | MIX Market loader | S-025 | Excel/ZIP | Static archive | agg.mfi_panel | 1999-2019 | None | S | P2 | Not started
PL-10 | FRED + Philly Fed + charge-off pullers | S-054/058 | FRED API + CSV | Free API key | agg.anchor_series | 1985+/2012+ | Quarterly | S | P1 | Not started
PL-11 | FFIEC/NCUA/FDIC pulls | S-055/056/057 | Bulk + REST API | FDIC API is no-auth | agg.bank_panel | Selective | Quarterly | M | P3 | Not started
PL-12 | EBA P3DH bulk downloader | S-045 | Bulk XBRL-CSV | New portal; DPM-aligned schema mapping needed | agg.irb_parameters | Jun-2025+ | Semiannual | M | P1 | Not started | Feeds AP-4
PL-13 | EBA stress/transparency/dashboard ingester | S-046/047/049 | CSV/Excel | Stable formats | agg.stress_results/bank_panel/stage_coverage | 2011+ | Per release | S | P2 | Not started
PL-14 | ECB SUP statistics pull | S-050 | ECB Data Portal API/CSV | SDMX available | agg.stage_coverage | 2015+ | Quarterly | S | P1 | Not started
PL-15 | Banca d'Italia recovery-series digitizer | S-053 (BdI row) | Excel appendix + PDF | Excel appendix published with note | agg.anchor_series | 2006-2024 | Annual | S | P2 | Not started
PL-16 | Benchmark-table digitizer (S&P/Moody's/GEMs/ICC/GCD studies) | S-031/032/034/036/038 | PDF tables -> anchor rows | Manual-assisted; provenance metadata per number | agg.anchor_series | Latest editions | Annual | M | P1 | Not started | Feeds AP-6
PL-17 | Scenario ingesters (Fed/EBA/BoE/RBI FSR/NGFS) | S-053/063/071/075 | CSV/portal downloads | NGFS via IIASA explorer; RBI annex is PDF | scen.macro_paths + scen.climate_paths | Current vintages | Per release | M | P1 | Not started
PL-18 | Brazil BCB SGS/SCR API puller | S-072 | REST API (no key) | python-bcb package | agg.em_comparators | 2012+ | Monthly | S | P3 | Not started | Also = pipeline design study
PL-19 | IMF FSI / BIS / OECD pulls | S-064/065/066 | SDMX / bulk CSV | Standard | agg.country_panel | Full | Quarterly | S | P2 | Not started
PL-20 | IBBI newsletter scraper — Table 5 + liquidation tables | S-079 | PDF table extract (pdfplumber/camelot) | Layout varies by edition; QA extracted totals vs published cumulative ratios | micro.default_events + micro.recovery_cashflows | 2017-2026 all quarters | Quarterly | M | P1 | Not started | FLAGSHIP — feeds AP-1
PL-21 | NeSL statistics digitizer | S-080 | PDF extract | Large PDFs (10MB+) | agg.india_anchor_series | All editions | Quarterly | S | P2 | Not started
PL-22 | Annexure V/VI collector (7 CRAs) | S-084 | Excel download + normalize | Naming/format differs per CRA; issuer-name entity resolution is the hard part | ref.ratings_history + micro.default_events | ~2016+ archives | Half-yearly | L | P1 | Not started | FLAGSHIP — feeds AP-2
PL-23 | NSE/BSE daily rating feed + Reg 57 ingester | S-083 | Feed Excel + announcements endpoints | NSE anti-bot (cookies/UA rotation); BSE simpler; PDFs need parsing for Reg 57 | ref.rating_events_daily | Aug-2025+ (older via announcements) | Daily | M | P1 | Not started
PL-24 | CIC defaulter-registry search protocol | S-081 | Throttled searches (Experian portal) | ToS-sensitive — legal review first; manual-assisted batches; CIBIL 403s bots | ref.entities + micro.default_events | Current stock | Quarterly | M | P3 | Not started | Name-matching to AP-2 corpus
PL-25 | NBFC AR ECL-note extractor (top 50) | S-101 | AR PDF -> stage tables (LLM-assisted + human QA) | Note formats vary; build extraction template per lender | agg.nbfc_ecl_panel | FY19-FY26 | Annual | L | P1 | Not started | FLAGSHIP — feeds AP-3
PL-26 | Bureau/industry PDF digitizer (CMI, MSME Pulse, CRIF, MFIN, Sa-Dhan, Equifax, FACE) | S-092..S-098 | PDF tables -> anchor rows | Backfill archives where hosted; else Wayback | agg.india_anchor_series + agg.india_geo_panel | 3-5y each | Quarterly | M | P1 | Not started
PL-27 | RBI FSR + T&P table extraction | S-075/076 | Manual download + extract | rbidocs is bot/CAPTCHA-gated — manual download step | agg.india_anchor_series + scen.macro_paths | 10y | Semiannual | M | P1 | Not started | Includes SMA + scenario annex
PL-28 | DBIE BSR-1 / sectoral deployment exports | S-077 | Portal CSV/XLSX | Portal quirks post-CIMS migration | agg.india_geo_panel | Full history | Quarterly | S | P1 | Not started | Feeds AP-5
PL-29 | SLBC PDF pilots (KL/PB/WB) | S-100 | PDF extract | Formats vary by state; district-name normalization | agg.india_geo_panel | 2-3y | Quarterly | M | P2 | Not started | Feeds AP-5
PL-30 | PTC rationale scraper (4 CRA sites) | S-102 | Rationale PDF scrape + parse | Volume; dedupe multiple reviews per pool | agg.pool_series_india | 3y pilot | Monthly | M | P2 | Not started
PL-31 | CGTMSE/MUDRA/NHB/NAFSCOB digitizers | S-086/087/088/089/091 | PDF/portal extract | Annual cadence, low volume | agg.india_anchor_series + idx.collateral_indices | 5-10y | Annual | M | P3 | Not started
PL-32 | P2P factsheet scraper | S-104 | Monthly PDF/page scrape | Formats vary by platform | agg.india_anchor_series | 2-3y | Monthly | S | P3 | Not started

## 5_DB_Schema
5. DATABASE SCHEMA — where everything lands
Target model: AnaCredit-shaped micro layer + openNPL-shaped default/recovery layer + long-format aggregate anchors. Doc §6.
ID | Layer | Schema.Table | Grain | Template basis | Key fields (illustrative) | Fed by (source IDs) | Status | Notes
T-01 | Reference | ref.entities | One row per obligor/entity | AnaCredit + RIAD | entity_id, name(s), LEI/CIN/PAN, sector, geography, size class | S-081, S-084, S-029, S-105 | Not started | Entity resolution backbone (India + global)
T-02 | Reference | ref.schemas | Documentation | AnaCredit, EBA NPL, Y-14 H.1, ESMA, CR6 | Field dictionaries + mappings | S-011, S-052, S-061 | Not started | Adopt, don't invent
T-03 | Micro | micro.facility_master | One row per facility at origination | AnaCredit instrument | facility_id, entity_id, product, orig_date, amount, rate, LTV, term, channel | S-001/002/007/012/014/103 | Not started
T-04 | Micro | micro.performance_monthly | Facility-month | AnaCredit + servicer templates | facility_id, month, balance, dpd, status, payment, utilization | S-001/002/007/014/019 | Not started | The panel layer
T-05 | Micro | micro.applications(_india) | One row per application | Home Credit / HMDA shape | app_id, applicant features, bureau features, decision, outcome | S-006/013/017/018/103 | Not started | Includes rejects where available
T-06 | Micro | micro.default_events | One row per default event | EBA NPL / openNPL | entity/facility_id, event_date, type (90dpd/insolvency/suit/rating-D), source | AP-1, AP-2, S-030 | Not started | Multi-source event table
T-07 | Micro | micro.recovery_cashflows | Event x cashflow | EBA NPL templates | event_id, date, amount, type (principal/interest/cost), channel, collateral | S-001/007/014, AP-1 | Not started | The LGD engine input
T-08 | Micro | micro.behavioural_panel / micro.transactions | Customer-month / transaction | — | customer_id, period, spend/payment/balance blocks | S-019/020/024 | Not started
T-09 | Aggregate | agg.anchor_series | Source x segment x metric x period | Long format | source_id, segment_json, metric, period, value, asof, url | AP-6 (many) | Not started | Backbone of Layer 2
T-10 | Aggregate | agg.irb_parameters | Bank x exposure class x PD band x ref date | Pillar 3 CR6 | bank, class, pd_band, EAD, wa_PD, wa_LGD, RW, EL | S-045/048 | Not started | Feeds AP-4 / M-12
T-11 | Aggregate | agg.stage_coverage | Country/entity x quarter | ECB SUP / EBA dashboard | scope, quarter, stage1/2/3 share, coverage | S-049/050, AP-3 | Not started | Include NBFC panel here too
T-12 | Aggregate | agg.india_anchor_series + agg.india_geo_panel | Segment/district x period | Long format | state/district, product, PAR/NPA metric, period, value | S-075..S-100 | Not started
T-13 | Aggregate | agg.card_trust_series / agg.pool_series(_india) | Pool x month | 10-D / rationale-derived | pool_id, month, chargeoff, delinq buckets, MPR/CCE, CE | S-009, S-102 | Not started
T-14 | Scenario | scen.macro_paths + scen.climate_paths | Scenario x variable x period | Fed/EBA/BoE/RBI/NGFS | scenario_id, variable, period, value, vintage | S-053/063/071/075 | Not started
T-15 | Index | idx.collateral_indices | Index x geography x period | — | index_id, geo, period, value | S-005/026/088 | Not started | HPI, Manheim, RESIDEX
T-16 | Meta | meta.source_registry + meta.load_log | Source / load event | This workbook | source_id, license, fetch date, rows, QA status | All | Not started | Mirror of 1_Sources for lineage

## 6_Anchors
6. KEY ANCHOR NUMBERS — calibration reference
Verified headline numbers with as-of dates. These are the targets synthetic books and models must reproduce. Full context in landscape doc.
ID | Theme | Metric | Segment / scope | Value | As-of | Source | Doc ref | Use in models
A-01 | India LGD | IBC recovery rate (realisation vs claims, annual) | India corporate, FY25 | ~37% | FY25 | RBI Trend & Progress (Dec-25) | §4.2 | Corporate LGD by channel
A-02 | India LGD | SARFAESI recovery rate | India, FY25 | 31.5% | FY25 | RBI T&P | §4.2 | Secured retail/SME LGD
A-03 | India LGD | Lok Adalat recovery rate | India, FY25 | 2.4% | FY25 | RBI T&P | §4.2 | Small-ticket LGD
A-04 | India LGD | IBBI cumulative realisation vs admitted claims | India CIRPs, cum. to Mar-26 | 30.6% | Mar-26 | IBBI quarterly newsletter | §4.2 | Corporate LGD level (cutoff-sensitive: 33.7% Jun-25)
A-05 | India LGD | IBBI realisation vs liquidation value / vs fair value | India CIRPs, cum. | 166.9% / 94.6% | Mar-26 | IBBI | §4.2 | Recovery vs collateral-value benchmarks
A-06 | India LGD | Avg time: closed liquidations | India | ~691 days | Mar-26 | IBBI | §4.2 | Discounting/workout duration
A-07 | India LGD | ARC security-receipt cumulative recovery | India SRs | 65-70% FY25E; 75-80% FY26E | Jun-25 | CRISIL SR study | §4.2 | Distressed secondary-market LGD
A-08 | Wholesale LGD | GCD LGD: unsecured / secured | Global wholesale | ~27% / ~22% | 2024 reports | GCD free library | §3.3 | Wholesale LGD priors
A-09 | Wholesale LGD | GCD LGD: senior / subordinated; time-to-recovery | Global wholesale | 26% / 38%; ~1.2y median | 2024 reports | GCD | §3.3 | Seniority splits, timing
A-10 | Wholesale LGD | Banca d'Italia bad-loan recovery rate | Italy, 2024 (series 2006+) | 41% avg (sec 44%, unsec 37%) | Dec-25 note | BdI Notes No. 48 | §3.3 | Workout-LGD time series; downturn evidence
A-11 | Wholesale LGD | NPL sale price vs GBV | Italy sofferenze / other NPE | 24% / 51% | 2024 | BdI No. 48 | §3.3 | Sale-vs-workout discount
A-12 | EM | GEMs private-counterpart default rate / recovery | EM, 1994-2024 | 3.54% / 72.9% | Oct-25 release | GEMs statistics | §2.7 | EM PD/LGD priors
A-13 | EM | GEMs public-counterpart default / recovery | EM sovereign-adjacent | 2.61% / 85.8% | Oct-25 | GEMs | §2.7 | Sovereign-adjacent priors
A-14 | Corporate PD | S&P 2024 global defaults; distressed-exchange share | Global corporates | 145 defaults; 59.3% DE | 2024 | S&P annual study (Mar-25) | §2.6 | TTC calibration; Gini 89.4%
A-15 | Corporate PD | Muni vs corporate senior unsecured recovery | US | ~67% vs ~47% | 2022 ed. | Moody's muni study | §2.6 | Low-default-portfolio LGD
A-16 | India PD | CRISIL 1-yr default rates by rating (approx) | India corporates | AAA ~0%; AA ~0.2%; A ~1.5%; BBB ~5%; <=BB >20% | FY24 study | CRISIL default study | §4.2 | India rating-PD mapping
A-17 | India PD | NeSL contractual default incidence | India corporate debt | ~3.75% of corporate debt | FY25 newsletters | NeSL | §4.2 | PD independent of NPA accounting
A-18 | India system | SCB GNPA | India system | 1.8% (multi-decadal low) | Mar-26 | RBI FSR Jun-26 | §4.4 | Baseline asset quality
A-19 | India stress | FSR baseline GNPA projection | India system | ~1.9% by Mar-28 | Jun-26 | RBI FSR | §4.4 | Baseline scenario target
A-20 | India stress | FSR severe-adverse: system CRAR; adverse GNPA | India system | CRAR 17.7% -> ~13.0%; adverse GNPA ~3.8-4.1% (v1, verify) | Jun-26 | RBI FSR | §4.4 | Severe-scenario validation target
A-21 | India staging | PSB retail SMA-0/1/2 share | India PSBs retail | 9.4% | Mar-26 | RBI FSR | §4.4 | SICR/staging calibration
A-22 | India staging | Large-borrower GNPA (CRILC) | India large borrowers | 1.2% | Mar-26 | RBI FSR | §4.4 | Wholesale staging anchor
A-23 | India sector | Agriculture GNPA (worst sector) | India | ~5.1% | Jun-26 FSR | RBI FSR | §4.4 | Sector heterogeneity
A-24 | India ECL | RBI ECL prudential floors | India banks | Stage-1 ~0.40%; Stage-2 ~5% | Apr-26 directions | RBI ECL Directions 2026 | §4.1 | ECL engine constraints
A-25 | India ECL | SICR presumption; effective date; glide path | India banks | 30 dpd; 1-Apr-2027; to FY2031 | Apr-26 | RBI ECL Directions | §4.1 | Build-target spec
A-26 | Microfinance | MFIN PAR 31-180 (cycle) | India MFI | 6.3% (Mar-25) -> 2.0% (Mar-26) | Q4 FY26 | MFIN Micrometer 57 | §4.3 | Full-cycle PD calibration
A-27 | Microfinance | Equifax MFI delinquency | India MFI | 6.64% (Mar-25) -> 2.35% (Mar-26) | Jun-26 | SIDBI-Equifax Pulse XXVII | §4.3 | Cross-check tracker
A-28 | Microfinance | Sa-Dhan PAR30+ / PAR90+ | India MFI, FY25 peak | 6.2% / 4.8% | FY25 | Sa-Dhan BMR 2025 | §4.3 | Stress-year calibration
A-29 | Retail India | CRIF retail PAR (all retail) | India retail | 3.1% (from 3.6% YoY) | FY26 | CRIF How India Lends May-26 | §4.3 | Retail book anchor
A-30 | Retail India | CIBIL CMI; home-loan delinquency | India retail | CMI 102; home 0.7-0.8% | Dec-25 data | TU CIBIL CMI Mar-26 | §4.3 | Product/tier anchors
A-31 | Digital PL | FACE fintech PL 90+ DPD | India digital PL | 3.6% (tier-3 4.2%) | Mar-25 | FACE quarterly | §4.3 | Digital-lending risk delta
A-32 | Housing India | HFC GNPA | India HFCs | 2.32% | Mar-24 | NHB T&P Housing | §4.4 | Housing anchor
A-33 | SHG India | SHG-BLP NPA | India SHG | 2.12% | FY24 | NABARD SoMFI | §4.3 | Group-lending anchor
A-34 | MSME India | Mudra PSB NPA | India micro-enterprise | 3.4% | FY24 | PQ answers | §4.2 | Micro-enterprise PD proxy
A-35 | NBFC ECL | Bajaj Finance Stage-3 PCR | India NBFC | 54% (FY25) -> 60% (FY26) | FY26 | Bajaj AR/presentations | §4.5 | NBFC coverage benchmark
A-36 | NBFC ECL | Chola Gross Stage 3 vs IRACP GNPA | India NBFC | GS3 2.81% vs GNPA 3.97% | Mar-25 | Chola AR + ECL doc | §4.5 | Ind-AS vs IRACP gap
A-37 | NBFC ECL | Shriram Gross/Net Stage 3 | India NBFC (CV) | 4.55% / 2.64% | Mar-25 | Shriram AR | §4.5 | CV segment anchor
A-38 | EU staging | EBA Stage-2 share: NFC / household | EU banks | 12.8% / 8.5% | Q1-26 | EBA Risk Dashboard | §3.1 | Stage-allocation benchmark
A-39 | US stress | DFAST projected losses (total / card / C&I / CRE) | US large banks | ~$708bn / ~$200bn / ~$160bn / ~$75bn | 2026 exercise | Fed DFAST | §3.2 | Stressed loss-rate anchors
A-40 | Stress tails | Peak NPL in systemic crises (median) | Advanced / EM economies | ~11% / ~30% | 1970-2025 | Laeven-Valencia 2026 | §3.6 | Severe/tail scenario anchor
A-41 | EAD | GP cardholders paying minimum (US) | US cards | 15% (highest since 2015) | 2025 report | CFPB CARD Act | §3.2 | Payment-rate/EAD anchor
A-42 | Trade finance | Trade product default rates | Global trade finance | <~0.3% | 2024 register | ICC Trade Register | §2.8 | Trade-book PD prior
A-43 | India write-offs | Bank write-offs (5y + H1 FY26) / FY16-FY25 | India | Rs 8.9 lakh cr / Rs 12.08 lakh cr | Dec-25 PQ | Lok Sabha / Rajya Sabha | §4.4 | Loss-flow context
A-44 | Securitisation | India securitisation volume | India, FY26 | Rs 2.55 lakh cr | Apr-26 | CRISIL PR | §4.6 | Pool-data sample size

## 7_Licensing
7. LICENSING REGISTER — check before you build on it
Summary judgements only — re-read source terms before any external release. Doc §8.
Source group | License / constraint | Prototype use | Commercial product | Redistribution | Notes
Fannie / Freddie / Ginnie | Free; terms restrict redistribution | OK | Review terms | No | Fine for internal prototypes; read terms before publishing derived data
Kaggle competition data (Amex, Home Credit, LTFS mirrors, GMSC) | Competition rules: academic/non-commercial | OK | No (without permission) | No | Prototype & teach yes; productize no
Bondora/Go&Grow, Berka, MIX Market, South German Credit | Open / CC BY 4.0 / research use | OK | Mostly OK (attribute) | CC BY: yes with attribution | MIX & South German are CC BY 4.0
NUS-CRI | Free with credentials; non-commercial only | OK | No (separate arrangement) | No | Commercial use needs agreement
Bureau/industry PDFs (CIBIL, CRIF, MFIN, Sa-Dhan, Equifax, FACE) | Copyrighted reports | OK (model from) | Derived models OK; tables no | No | Don't republish extracted tables
CRA disclosures (Annexure V/VI, studies, rationales) | Public regulatory disclosures | OK | Derived datasets: cite | Avoid wholesale republication | SEBI-mandated transparency
Government/regulator open data (RBI, IBBI, NeSL, CGTMSE, SEC, SBA, Fed, FDIC, NCUA, data.gov.in, IMF, BIS, WB, EBA, ECB) | Public domain / open government | OK | OK | Generally OK (attribute) | The safest layer
GCD / Japan CRD raw pools | Members only (regulated lenders, give-to-get) | Via member bank only | Via member bank only | No | Free summary reports usable as priors
Moody's / S&P / Fitch studies | Copyright; free access | OK (cite) | Cite; don't reproduce tables | No | Digitize numbers with provenance
Moody's DRD / S&P CreditPro / Trepp / LCD / Orbis | Paid licenses | If licensed | If licensed | No | Check WRDS/university access first
CIC defaulter registries (search portals) | Public dissemination, search-only; ToS on scraping | Careful (legal review) | Careful | No bulk republication | Throttled, documented protocol; Experian most tolerant
Manheim index | Free download, no formal open license | OK | Review | No | Cox Automotive property
EDW | Registration; bulk paid | Templates: OK | Data: license needed | No | Use ESMA templates as free schema
P2P platform disclosures | RBI-mandated public disclosure | OK | Cite platform | No | Aggregate series fine

## 8_Watchlist
8. WATCHLIST — unverified items & upcoming releases
Things to re-check plus the release calendar that should trigger refreshes.
ID | Item | Type | Expected / check date | Action needed | Priority | Status | Notes
W-01 | FSR Jun-2026 adverse-scenario GNPA print (v1 carried 3.8-4.1%) | Unverified | Aug-2026 | Open FSR PDF, confirm adverse GNPA path | P1 | Not started | rbidocs bot-gated - manual download
W-02 | Moody's annual default study 2026 edition (2025 data) | Unverified | Check now | Locate via ratings.moodys.com registration or mirror | P2 | Not started
W-03 | NABARD Status of Microfinance FY25 edition | Unverified | Sep-2026 | Check nabard.org publications | P3 | Not started
W-04 | Equifax India defaulter search portal | Unverified | When needed | Locate portal or confirm absence | P3 | Not started
W-05 | Mintos loan-book export current availability | Unverified | When needed | Login and check export | P3 | Not started
W-06 | ECGC annual-report claims data (export-credit loss proxy) | Unverified | Sep-2026 | Pull latest ECGC AR; extract claims vs premium | P3 | Not started | §5.1 addition
W-07 | ELFA MLFI-25 / Equifax SBLI / KC Fed / Moody's project finance current editions | Unverified (§2.11) | Sep-2026 | Re-verify sources and access | P3 | Not started | Added from coverage audit
W-08 | Fitch study access route (registration) | Unverified | When needed | Register and confirm downloads | P3 | Not started
W-09 | MFIN Micrometer 58 (Q1 FY27) | Upcoming release | ~Sep-2026 | Ingest into PL-26 | P2 | Not started
W-10 | CRISIL default & transition study FY2026 | Upcoming release | ~Dec-2026 | Digitize into anchors | P2 | Not started
W-11 | RBI FSR Dec-2026 | Upcoming release | ~Dec-2026 | Update anchors + scenario annex | P1 | Not started
W-12 | RBI T&P 2025-26 (recovery-by-channel FY26) | Upcoming release | ~Dec-2026 | Update A-01..A-03 | P1 | Not started
W-13 | EBA P3DH full-year 2025 ref-date data + 2026 dates | Upcoming release | H2-2026 | Extend AP-4 panel | P1 | Not started
W-14 | NGFS Phase VI (physical-risk overhaul) | Upcoming release | End-2026 | Re-run climate overlays on Phase VI | P2 | Not started | Time climate work accordingly
W-15 | BoE 2026 desk-based stress test publication | Upcoming release | Q4-2026 | Ingest aggregate results | P3 | Not started
W-16 | EBA Transparency Exercise Dec-2026 | Upcoming release | Dec-2026 | Refresh bank panel | P2 | Not started
W-17 | RBI final Model Risk Management guidance (post-consultation) | Upcoming release | H2-2026? | Align validation-doc templates | P2 | Not started | Draft closed Jul-2026
W-18 | RBI climate disclosure framework finalization / scenario guidance | Upcoming release | Unknown | Track; RB-CRIS phase-2 | P3 | Not started